## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | Generate recorded calls between sales representative and customer for initial dataset. | MUST HAVE | - | Arya | 3- Completed
1 | 1 | US-02 | Develop transcription engine to convert .wav audio files into clean text. | MUST HAVE | 1 | Arya | 3- Completed
2 | 2 | US-03 | Implement Live Speech-to-Text for real-time customer input capture. | MUST HAVE | 1 | Arya | 3- Completed
2 | 2 | US-04 | Integrate heuristic speaker diarization to distinguish Agent vs. Customer. | MUST HAVE | 2 | Arya | 3- Completed
2 | 2 | US-05 | Add functionality to download transcribed text as a .txt file for record keeping. | SHOULD HAVE | 2 | Arya | 3- Completed
3 | 3 | US-06 | Implement LLM-based Sentiment, Intent, and Entity Extraction for customer snippets. | MUST HAVE | 2 | Arya | 3- Completed
4 | 4 | US-07 | Integrate all features into a single Streamlit UI with real-time AI sales suggestions and objection handling. | MUST HAVE | 1,2,3 | Arya | 3- Completed
4 | 4 (Final) | US-08 | Optimize application state management and provide multi-engine (Gemini/Groq) support. | MUST HAVE | US-07 | Arya | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[9 empty] | 18 | 9 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Find suitable sources and record sales calls manually for initial dataset. | 2025-10-16 | 2025-10-20 | Arya | Research | 3- Completed | 3 | Day 1: 1; Day 2: 2
US-02 | T-02 | Implement SpeechRecognition and pydub to convert .wav files to text. | 2025-10-21 | 2025-10-24 | Arya | Coding | 3- Completed | 6 | Day 1: 2; Day 2: 2; Day 3: 2
US-03 | T-03 | Develop sounddevice capture logic for 5s live recording windows. | 2025-11-12 | 2025-11-15 | Arya | Coding | 3- Completed | 6 | Day 1: 2; Day 2: 2; Day 3: 2
US-04 | T-04 | Create keyword-based role assignment logic (e.g., "price", "buy"). | 2025-11-16 | 2025-11-19 | Arya | Coding | 3- Completed | 4 | Day 1: 2; Day 2: 2
US-06 | T-05 | Design LLM system prompt to enforce strict JSON output for Sentiment/Entities. | 2025-11-25 | 2025-11-30 | Arya | Coding | 3- Completed | 7 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 1
US-07 | T-06 | Build 3-column analysis UI and Chat Bubbles in Streamlit using Custom CSS. | 2025-12-01 | 2025-12-10 | Arya | UI Design | 3- Completed | 9 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 1
US-08 | T-07 | Fix AttributeError by initializing st.session_state.transcript in startup logic. | 2025-12-18 | 2025-12-18 | Arya | Bug Fix | 3- Completed | 2 | Day 1: 2
US-08 | T-08 | Integrate Groq (Llama 3.3) and Gemini 2.5 Flash for high-speed analysis. | 2025-12-18 | 2025-12-19 | Arya | Integration | 3- Completed | 7 | Day 1: 2; Day 2: 3
US-08 | T-09 | Implement legacy_rule_engine fallback for API/Network resilience. | 2025-12-19 | 2025-12-19 | Arya | Coding | 3- Completed | 3 | Day 1: 3

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2025-10-16 | Difficulty obtaining a clean, labeled dataset for initial training. | Began work by manually labeling a small subset of sample sales calls to seed the model.
1 | 2025-10-24 | Initial STT output has high word error rate for fast speech. | Added 2-minute clean audio clips to the training set and optimized speech parameters.
2 | 2025-11-19 | Transcript lacks clarity on who is speaking (Agent vs. Customer). | Added keyword-based heuristic diarization and tested initial speaker labels.
2 | 2025-11-22 | UI is purely functional and lacks intuitive sales-assistance cues. | Started implementing the modern SaaS UI and established the 3-column analysis grid.
3 | 2025-11-29 | Basic analysis fails to capture subtle customer sentiment/emotions. | Implemented deeper emotion detection prompts within the LLM analysis loop.
4 | 2025-12-03 | Fragmentation between STT, Analysis, and UI components. | Integrated all three milestones into a unified Streamlit interface for testing.
4 (Fix) | 2025-12-18 | Application crashes (AttributeError) when navigating to the Upload page. | Initialized st.session_state.transcript at the app root to ensure state persistence.
4 (Final) | 2025-12-19 | Gemini latency issues during peak usage. | Integrated Groq (Llama 3.3) as a lightning-fast alternative engine for real-time suggestions.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-10-16 | 2025-10-24 | Arya | Data Collection & Audio Setup | Manual transcription | Researching STT models | Researched Google STT & configured initial audio processing.
2 | 2 | 2025-11-12 | 2025-11-19 | Arya | Live Speech capture | Data Collection | Speaker Diarization logic | Researched en-IN accents & started coding the live co-pilot module.
3 | 3 | 2025-11-25 | 2025-12-05 | Arya | Intent & Entity analysis | Sequential processing | Developing Streamlit UI | Added features for customer text extraction and JSON output formatting.
4 | 4 | 2025-12-06 | 2025-12-10 | Arya | AI Suggestion Engine | Developing UI | AI analysis refinement | Added Gemini/Groq integration for real-time sales recommendations.
5 | 4 (Fix) | 2025-12-11 | 2025-12-19 | Arya | Session State Management | Hardcoding local paths | Cross-platform testing | Resolved AttributeError: transcript by properly initializing session state variables.
6 | 4 (Final) | 2025-12-18 | 2025-12-19 | Arya | Multi-Engine Support (Gemini & Groq) | Single-provider dependency | Rule-based fallbacks | Optimized the real-time response pipeline and added legacy_rule_engine for high reliability.

## Unit Test Plan
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
SI: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
1 | Speech-to-Text Conversion (File Upload) | Upload a WAV file in the "File Analysis" tab and click "Start Processing". | System should split audio into chunks and convert to text without failure. | Clean, accurate transcript is generated for all audio segments. | PASSED: Accurate transcript generated using pydub chunking and Google STT.
2 | Live Speech to Text | Navigate to "Live Co-Pilot", click "Record", and speak for 5 seconds. | Mic captures live audio and converts the chunks to text output. | Accurate, real-time transcription of user speech with minimal latency. | PASSED: Successfully captured via sounddevice and transcribed with en-IN support.
3 | Heuristic Role Detection | Process a multi-speaker audio file in the "Upload" tab. | System should assign roles based on keywords like "want", "price", or "hello". | Accurate labeling of "Customer" vs "Sales Agent" in the chat feed. | PASSED: Keywords correctly trigger role assignment in the transcript loop.
4 | LLM Analysis (Gemini/Groq) | Trigger analysis for customer text via the Live or Upload interface. | LLM should return a structured JSON with Sentiment, Intent, and Entities. | Correct emotion, intent, and entity labels are returned in JSON format. | PASSED: Analysis complete; data correctly parsed into the 3-column UI layout.
5 | AI Sales Suggestion | Review the suggestion box after a customer input is analyzed. | System should return context-appropriate sales recommendations. | Relevant suggestions, such as follow-up questions or product recommendations. | PASSED: Suggestions and Strategy displayed clearly in themed suggestion boxes.
6 | Session State Persistence | Switch between "Live Co-Pilot" and "File Analysis" tabs multiple times. | Session state should persist and not throw AttributeError for 'transcript'. | Smooth navigation between pages without app crashes or loss of data. | PASSED: Verified; st.session_state.transcript is initialized at startup.
7 | API Fallback Logic | Provide an invalid API key or simulate a network failure and trigger analysis. | System should trigger legacy_rule_engine when the API call fails. | Application provides basic rule-based analysis instead of crashing. | PASSED: Rule-based fallback active; provides basic intent and entities accurately.

## Defect Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
SI No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Arya | 2025-10-23 | Live speech transcription misses or misinterprets words during fast-paced conversations | 1 | Arya | Logical | Configured recognize_google with language="en-IN" and implemented 5-second sounddevice capture intervals. | 2025-10-25 | Closed | Regional accent support (en-IN) significantly improved transcription accuracy for Indian users.
2 | Arya | 2025-11-06 | Delay in converting long audio recordings into text during upload analysis | 1 | Arya | Standards | Integrated Groq (Llama 3.3 70B) for "lightning-fast" analysis to offset the latency of the transcription engine. | 2025-11-08 | Closed | Analysis is now near-instant; Groq's high throughput manages large transcripts without bottlenecking.
3 | Arya | 2025-10-28 | Background noise affects transcription accuracy in recorded calls | 2 | Arya | Logical | Implemented split_on_silence using pydub with a -16 dBFS threshold to isolate clean voice segments. | 2025-11-01 | Closed | Filtering silence and noise spikes before transcription reduced "hallucinated" words in the output.
4 | Arya | 2025-11-19 | Speaker diarization fails to correctly distinguish between multiple speakers | 2 | Arya | Logical | Added keyword-based logic (e.g., "i want", "price") to heuristically assign roles to "Customer" or "Sales Agent". | 2025-11-22 | Closed | Stable alternative to complex diarization; accurately labels speakers based on sales-intent keywords.
5 | Arya | 2025-11-19 | System fails to accurately extract entities from transcribed call data | 3 | Arya | Logical | Developed a structured System Prompt that enforces a strict JSON schema for Sentiment, Intent, and Entities. | 2025-11-25 | Closed | Enforcing json_object response format ensures consistent parsing of Brand, Product, and Budget.
6 | Arya | 2025-12-05 | AI suggestions are not updated in real time based on latest customer responses | 4 | Arya | Maintainability | Utilized st.session_state.live_transcript to append and display analysis immediately after the 5s recording window. | 2025-12-07 | Closed | Session state persistence ensures the "Co-Pilot Feed" updates without refreshing the entire page.
7 | Arya | 2025-12-18 | AttributeError: transcript when navigating to Upload page before Live page | 4 | Arya | Logical | Explicitly initialized st.session_state.transcript = [] at the top level of the application logic. | 2025-12-18 | Closed | Resolved the state-dependency bug; the application now handles page navigation gracefully.
8 | Arya | 2025-12-18 | Analysis fails gracefully when API keys are missing or invalid | 4 | Arya | Reliability | Built a legacy_rule_engine fallback that uses regex to provide basic insights if the LLM API call fails. | 2025-12-19 | Closed | Ensures the UI remains functional and provides basic value even during network or API outages.